## Sheet1
| 2024-08-20 | 2024-08-27 | 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | Key
Basic Page Layouts | [13 empty] | Web App | bar: 2024-08-20 to 2024-09-24; 2024-10-08 to 2024-10-15
Backend for each Page | [13 empty] | Data Server | bar: 2024-08-27 to 2024-09-24; 2024-10-08 to 2024-10-15
Search Engine Functionality | [13 empty] | Mobile App | bar: 2024-09-24 to 2024-10-15
Check-out for items | [13 empty] | ML Model | bar: 2024-10-08 to 2024-10-29
Web-app Validation | [13 empty] | Completed | bar: 2024-10-29 to 2024-11-12
In Progress
SQLite Database Created | [13 empty] | Not Started | bar: 2024-08-20 to 2024-10-01
Getting a working server | [13 empty] | Behind Schedule | bar: 2024-09-24 to 2024-11-05
Python script to populate database | bar: 2024-10-08 to 2024-10-29
Relationships Between Data (Queries) | bar: 2024-10-08 to 2024-11-12
Database Server Validation | bar: 2024-10-22 to 2024-11-12
Create App and Functional Simulation | bar: 2024-08-27 to 2024-09-03
Create UI for each page | bar: 2024-09-03 to 2024-09-24; 2024-10-08 to 2024-10-15
Add functionality using SQLite database | bar: 2024-09-17 to 2024-09-24; 2024-10-08 to 2024-10-15
Search Database and Check Out Functionality | bar: 2024-09-24 to 2024-10-15
Track Which Users Have Checked Out/In Items | bar: 2024-10-22 to 2024-10-29
Mobile App Validation | bar: 2024-10-29 to 2024-11-12
Watch Youtube Videos on ML/Nueral Networks | bar: 2024-08-20
Choose ML Model and Finalize Code | 2024-08-27: REDONE
Finalize Dummy Data Sets | bar: 2024-09-24 to 2024-10-08
Create a Working Automation Function | bar: 2024-10-08 to 2024-10-22
ML Model Validation | bar: 2024-10-15 to 2024-11-12
ConOps Project Report | 2024-08-20: DUE SEP 15
FSR, ICD, Milestones, Plan | 2024-08-20: DUE SEPT 26
Project Introduction Presentations | 2024-08-20: PRESENT ON SEPT 24
Project Update Presentations | 2024-08-20: PRESENT ON OCT 14 - 23
Final Presentations | 2024-08-20: PRESENT ON NOV 11-20
Final Report | 2024-08-20: DUE DEC 5