## 403
| 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | Key
Website Hosting | [11 empty] | Web App | bar: 2025-01-13 to 2025-01-20
Connection to Database | [11 empty] | Data Server | bar: 2025-01-27 to 2025-02-03
Fitting data to app's uses | [11 empty] | Mobile App | bar: 2025-02-10 to 2025-02-24
ML Model
Connect to website | [11 empty] | Group | bar: 2025-01-13 to 2025-02-03
Connect to app | [11 empty] | Completed | bar: 2025-01-27 to 2025-02-03
Allow interactions between ML and DB | [11 empty] | In Progress | bar: 2025-02-10 to 2025-03-03
Not Started
Align app database tables with external database | [11 empty] | Behind Schedule | bar: 2025-01-13 to 2025-01-20
Connect to Database | bar: 2025-01-27 to 2025-02-10
Create backend for ML model use | bar: 2025-02-03 to 2025-02-17
Check-in/check-out process using ML | bar: 2025-02-24 to 2025-03-03
Refitting + Adding more categories | bar: 2025-01-13 to 2025-01-20
Connection to Mobile App | bar: 2025-01-27 to 2025-02-10
Validation with physical objects | bar: 2025-02-17 to 2025-03-03
Weave the web that connects each subsystem | bar: 2025-01-13 to 2025-02-03
Get images and example products from lab | bar: 2025-02-03
Testing using phone and computer | bar: 2025-02-10 to 2025-02-17
Full-system Validation | bar: 2025-02-24 to 2025-03-24
Final Presentation | 2025-01-13: April 9th
Final Demo | 2025-01-13: April 21st
Final Report | 2025-01-13: April 28th